# Secure Upload Gateway — Build Plan, Parts 1–5

Sep 22, 2026

## Source documents

Only one of the three named sources is available in this conversation. The plan below is built on it, and every place where the other two might have decided something differently is marked as an open question.

| Source | Status | Used as |
| --- | --- | --- |
| Secure File Upload Security Gateway — Research-Backed Project Specification | Read in full (35 sections) | Primary source of truth for architecture, schema, API, IAM, lifecycle, tests, cost |
| Secure_File_Upload_Gateway_Full_Literature_Survey.docx | Not attached to this conversation; no file was found in the uploads area | Not used. Attach it and I will reconcile any conflicts before Phase 0 |
| secure-upload-gateway-stage1.md | Not attached | Not used. Same |

Facts were verified on 22 September 2026 against official documentation and package registries. Where a page could not be opened the item is marked UNVERIFIED in Part 3 and the plan does not depend on it.

## Part 1 — Architecture and decision freeze

The architecture from the specification is frozen unchanged: eight trust zones, four Node.js services sharing one PostgreSQL database, a job queue in PostgreSQL, decisions bound to (bucket, key, version_id, sha256, size), a promotion service that is the only writer of trusted storage, and a write-once ciphertext replica on Google Cloud. Six implementation decisions change because verification showed the original choice is no longer obtainable, deprecated, or incompatible; each is marked CHANGED below with evidence.

### 1.1 Frozen architecture

flowchart LR
  C[Client app<br/>Z1 untrusted] -->|API key / upload token| A[api<br/>Fastify, UPLOAD_ROLE]
  A -->|PutObject If-None-Match| Q[(quarantine bucket<br/>versioned)]
  A --> DB[(PostgreSQL 18<br/>jobs + evidence)]
  S[scanner<br/>SCANNER_ROLE] -->|GetObject by VersionId| Q
  S --> CL[clamd 1.4 LTS<br/>+ YARA-X CLI]
  S --> DB
  P[promotion<br/>PROMOTION_ROLE] -->|GetObject by VersionId,<br/>re-hash, AES-256-GCM| T[(clean bucket<br/>ciphertext)]
  P --> DB
  R[replication<br/>REPLICATION_ROLE] -->|WIF, ifGenerationMatch=0| G[(GCS replica<br/>ciphertext)]
  R --> DB
  D[dashboard<br/>Next.js 16, read-only] -->|JWT| A

Invariants that no later phase may weaken:

- A file reaches the clean bucket only through services/promotion, only after an un-superseded ALLOW decision, and only after the promoter has re-fetched the bound version and re-verified SHA-256 and size.

- services/api and services/scanner hold no credential that can write the clean bucket or insert a security_decisions row.

- Every state transition of a file writes one hash-chained audit_events row in the same database transaction.

- Every failure path ends in ERROR, QUARANTINE or BLOCK; no code path maps an exception to ALLOW.

- Clean and replica storage contain only the SUG1 envelope format; the KEK exists only in the promotion and download processes.

### 1.2 Decision register

Status values: APPROVED (kept from the specification), CHANGED (replaces a specification decision, evidence given), OPEN (needs your answer before Phase 0).

| ID | Decision | Reason | Alternatives considered | Evidence | Status | Impacted components |
| --- | --- | --- | --- | --- | --- | --- |
| DEC-001 | Job queue in PostgreSQL using SELECT … FOR UPDATE SKIP LOCKED; no Redis, SQS or Kafka in the MVP | One data store to secure and back up; queue rows are already evidence; throughput needs are tens of files per minute | Redis + BullMQ; SQS; pg-boss library | PostgreSQL SELECT documents SKIP LOCKED | APPROVED | scanner, promotion, replication |
| DEC-002 | Local S3-compatible store is LocalStack Community (localstack/localstack:2026.08.3), not MinIO | The MinIO repository is archived, community binaries are source-only, and the minio/minio Docker Hub repository returns 404 as of September 2026. LocalStack Community supports versioning and If-None-Match on PutObject (since v3.7.0) and If-Match (4.0.3) | MinIO built from archived source (unpatched CVE, maintenance burden); AIStor Free (proprietary licence file, single node); SeaweedFS 4.45 (Apache-2.0, versioning, conditional headers; lighter but a less faithful S3 emulation); Garage (no versioning); RustFS (pre-release) | MinIO README; LocalStack v3.7.0; LocalStack S3 docs; SeaweedFS S3 API | CHANGED (spec said MinIO) | Compose, packages/storage, local IAM tests |
| DEC-003 | Local privilege separation is enforced by application credentials (each service has only its own access key pair) and verified for real on AWS; LocalStack Community is not relied on to enforce IAM policy | IAM policy enforcement in LocalStack is a paid-tier feature to the best of current knowledge (VERIFICATION REQUIRED in Phase 2); SeaweedFS offers per-identity bucket actions if enforcement locally becomes mandatory | Run IAM negative tests only on AWS (chosen); switch to SeaweedFS with -s3.config identities | LocalStack docs above | CHANGED (spec ran IAM tests on MinIO users) | tests/security/iam |
| DEC-004 | Dashboard is Next.js 16 (App Router, TypeScript, Tailwind 4, shadcn/ui), served as a separate container that only calls the Fastify API | You asked for Next.js; the specification chose React+Vite to avoid a second server. The trade-off is accepted with two constraints: no security logic, no direct database access, and all data fetching from the browser or from Route Handlers that forward the user's JWT; the Next server holds no secrets | React + Vite static SPA (spec) | Next.js 16 installation (Node 20.9+, Turbopack default, next.config.ts); Tailwind v4 + Next; shadcn Next install | CHANGED | apps/dashboard |
| DEC-005 | PostgreSQL 18 (postgres:18-alpine) | 18.6 is a year old, supported to November 2030, adds native uuidv7() for time-ordered IDs; all syntax used (identity columns, SKIP LOCKED, pgcrypto digest, citext, advisory locks) is unchanged. Note: PG 18 generated columns default to VIRTUAL; the schema uses none | PostgreSQL 16 (spec; supported to November 2028, no advantage now); 17 | PostgreSQL releases; PG 18 release notes | CHANGED (spec said 16; your brief also said 16 — say if you want 16 kept) | migrations, Compose |
| DEC-006 | Metrics library is @prometheus-io/client 0.16.x | prom-client 15.1.3 is marked deprecated on npm in favour of @prometheus-io/client | prom-client | npm registry deprecation notice (Part 3) | CHANGED | packages/shared/metrics |
| DEC-007 | TypeScript pinned to 6.0.3; ESLint 10 flat config; typescript-eslint 8.70 | TypeScript 7.0 (native port) ships no programmatic API yet and typescript-eslint's peer range is <6.1.0; ESLint 9 reached end of life on 6 August 2026 | TS 7 with typescript@npm:@typescript/typescript6 alias; TS 5.9.3 | TypeScript 7.0 announcement; typescript-eslint versions; ESLint v10 | CHANGED (spec said TypeScript 5) | all packages |
| DEC-008 | Node.js 24 LTS everywhere; images node:24-alpine; pnpm 12 installed with npm i -g pnpm@12 in Dockerfiles (Corepack is still bundled in Node 24 but removed from Node 25+) | Active LTS until October 2026, maintenance to April 2028; every chosen library requires Node ≥ 22 | Node 26 (Current, LTS from 28 October 2026) | Node.js releases; Corepack README | APPROVED | all |
| DEC-009 | Fastify 5.12 with @fastify/type-provider-zod 1.0 and zod 4.6; raw application/octet-stream upload body; no multipart parser | Fastify 5 is the current stable, tested on Node 24; the scoped type provider is the org-official package and requires zod ≥ 4.2 | Express + multer (10 advisories in 2025–2026); unscoped fastify-type-provider-zod | Fastify LTS; npm registry | APPROVED | services/api |
| DEC-010 | ClamAV 1.4.6 LTS image clamav/clamav:1.4.6, configured through CLAMD_CONF_<Option> environment variables; in-house 60-line INSTREAM client | 1.4 is the LTS line (EOL 15 August 2027); the official image documents env-var overrides; the clamscan npm package has had no release since October 2024 | ClamAV 1.5.4 (regular release, shorter support); clamscan npm | ClamAV EOL policy; ClamAV Docker; clamd protocol | APPROVED (version pinned) | services/scanner, Compose |
| DEC-011 | YARA-X 1.20.0 CLI (yr scan --output-format ndjson) invoked as a subprocess; results parsed from NDJSON, never from the exit code | YARA-X has no distinct "match found" exit code (only 0 or 1 for error); the official @virustotal/yara-x npm package is a WebAssembly build with no production-readiness statement | @virustotal/yara-x WASM (fallback if subprocess cost matters); classic YARA (maintenance mode) | YARA-X CLI; cli/src/main.rs | APPROVED (invocation detail added) | services/scanner |
| DEC-012 | Application-level envelope encryption, AES-256-GCM, per-file DEK, KEK from a Docker secret locally and SSM SecureString in the cloud; KMS optional | As in the specification; verified createCipheriv('aes-256-gcm', key, iv, {authTagLength: 16}) and that authenticity is established only at decipher.final() | KMS-only; SSE-KMS only | Node.js crypto; SP 800-38D | APPROVED | packages/crypto |
| DEC-013 | Terraform 1.16 with AWS provider 6.x and Google provider 8.x; bootstrap IAM access keys are created with the AWS CLI, not Terraform | AWS provider 6 is current; aws_iam_access_key writes the secret to state in plaintext and aws_ssm_parameter SecureString values also land in state unless value_wo is used | OpenTofu 1.12 (MPL-2.0, drop-in) if the BUSL licence is a concern; pgp_key on aws_iam_access_key | AWS provider 6 upgrade guide; aws_iam_access_key | APPROVED (key handling added) | infrastructure/ |
| DEC-014 | The GCP project is created once by hand (gcloud projects create) and referenced by Terraform, not created by Terraform | The Google provider docs say google_project must belong to an Organization, while the API allows a parentless project on a personal account; Terraform creation of a parentless project is UNVERIFIED | google_project resource | google_project; Creating projects | APPROVED | infrastructure/gcp |
| DEC-015 | Workload Identity Federation from the laptop uses STS session credentials exported as AWS_ACCESS_KEY_ID, AWS_SECRET_ACCESS_KEY, AWS_SESSION_TOKEN, AWS_REGION; no IMDS, no Google service-account key | Google's auth libraries read AWS environment variables before falling back to the metadata server; the credential configuration file contains no secrets | Executable-sourced credentials; service-account key file (rejected) | WIF with AWS; AIP-4117 | APPROVED | services/replication |
| DEC-016 | The DenyOverwrite bucket-policy statement (Null: s3:if-none-match) is applied to both quarantine and clean buckets; CopyObject is never used | AWS documents that enforcing s3:if-none-match makes CopyObject fail (403 without headers, 501 with); the promoter streams through itself and never copies server-side | Skip the statement and rely on code | Enforcing conditional writes | APPROVED (constraint recorded) | bucket policies, promotion |
| DEC-017 | Billing alarm on AWS/Billing EstimatedCharges is created with a us-east-1 provider alias after "Receive Billing Alerts" is switched on manually in the console | The metric exists only in us-east-1 and needs the console preference first | Budgets only | Billing alarm docs | APPROVED | infrastructure/aws/budgets.tf |
| DEC-018 | Local TLS: the API listens on plain HTTP inside the Compose network; a Caddy 2.11 container with tls internal is added only in the tls Compose profile | Caddy cannot install its root CA into the host trust store from a container; plain HTTP keeps CI simple. Cloud demo still uses TLS to AWS and GCP from the SDKs | Always-on Caddy | Caddy tls directive | APPROVED (spec said Caddy always on; profile-gated now) | Compose |
| DEC-019 | Local GCS emulation is fsouza/fake-gcs-server:1.56.1 through the JSON API only | It honours ifGenerationMatch, generations and declared CRC32C on JSON uploads; the XML path does not | Google storage-testbench | fake-gcs-server upload.go | APPROVED | Compose, packages/storage |
| DEC-020 | Argon2id via native argon2 0.45 (prebuilt Node-API binaries); @node-rs/argon2 is the fallback if a platform lacks a prebuild | Both verified on Node 24 | bcrypt | npm registry, node-argon2 README | APPROVED | services/api |
| DEC-021 | ZIP inspection with yauzl 3.4 (lazy central-directory reading) plus own structural checks; @zip.js/zip.js 2.17 is the alternative | yauzl is maintained (June 2026 release) and streams entries without extraction | @zip.js, unzipper, node-stream-zip | npm registry | APPROVED | packages/security-engine/archive |
| DEC-022 | Vitest 5, k6 2.2, testcontainers 12 optional | Current versions; Vitest 5 defaults clearMocks: true | Jest | Vitest 5 blog | APPROVED | tests/ |

### 1.3 Open questions to settle before Phase 0

| ID | Question | Default if unanswered |
| --- | --- | --- |
| OPEN-1 | Keep PostgreSQL 18 (DEC-005) or revert to 16 as your brief states? | 18 |
| OPEN-2 | LocalStack Community (S3 fidelity, larger image, IAM likely not enforced) or SeaweedFS (lighter, per-identity actions) for local storage? | LocalStack, re-evaluated after the Phase 2 spike |
| OPEN-3 | Attach the two missing source documents so conflicts can be reconciled? | Proceed on the specification alone |
| OPEN-4 | Windows development host: Docker Desktop with WSL 2 backend assumed; confirm | Assumed |

### 1.4 Final technology stack

| Layer | Choice | Version |
| --- | --- | --- |
| Runtime | Node.js | 24 LTS (image node:24-alpine) |
| Package manager | pnpm | 12.5 |
| Language | TypeScript | 6.0.3 (pinned) |
| API | Fastify, @fastify/type-provider-zod, @fastify/rate-limit, @fastify/helmet, @fastify/cors, @fastify/cookie, @fastify/swagger | 5.12 / 1.0 / 11.2 / 13.1 / 11.3 / 11.1 / 9.8 |
| Validation | zod | 4.6 |
| Database | PostgreSQL; pg; kysely; node-pg-migrate | 18 / 8.23 / 0.29 / 9.0 |
| Logging and metrics | pino; @prometheus-io/client | 10.3 / 0.16 |
| Auth | jose (EdDSA); argon2 | 6.2 / 0.45 |
| Files | file-type; yauzl; sharp | 22.1 / 3.4 / 0.35 |
| Scanning | ClamAV; YARA-X | 1.4.6 / 1.20.0 |
| Cloud SDKs | @aws-sdk/client-s3, client-sts, client-ssm, credential-providers; @google-cloud/storage; google-auth-library | 3.1137 / 8.2 / 11.1 |
| Local emulation | LocalStack Community; fake-gcs-server | 2026.08.3 / 1.56.1 |
| Dashboard | Next.js; React; Tailwind; shadcn | 16.3 / 19.3 / 4.3 / CLI 4.21 |
| Infra | Docker Compose v2; Terraform; AWS provider; Google provider | current / 1.16 / 6.58 / 8.1 |
| Tests | Vitest; k6; ESLint; typescript-eslint | 5.0 / 2.2 / 10.11 / 8.70 |

## Part 2 — Complete implementation roadmap

The 66 requested phases collapse into 36 phases, because several of them are one pull request's worth of work and splitting them would create phases with no independent Definition of Done. Nothing is dropped: the mapping table shows where each of the 66 lands. Each phase gets its full contract (the 26 fields A–Z) when you say "START PHASE n"; here every phase has its objective, inputs, outputs, dependencies, security and research objective, Definition of Done and commit message, which is enough to plan and to review scope.

### 2.1 Mapping of the 66 requested phases

| Requested | Lands in | Why |
| --- | --- | --- |
| 0 Architecture freeze | P0 | As requested |
| 1 Repository, 2 Docker Compose | P1, P2 | Kept separate: P2 includes the storage-emulator spike that decides OPEN-2 |
| 3 Database and migrations, 4 Config and secrets | P3, P4 | As requested |
| 5 Fastify foundation, 44 Health and readiness | P5 | Health endpoints are part of the first bootable server |
| 6 Application authentication, 7 RBAC | P6 (API keys), P7 (users, JWT, RBAC) | As requested |
| 8 Upload session, 9 Quarantine storage, 10 Streaming and limits | P8 (session + policy pre-check), P9 (storage provider + quarantine bucket), P10 (streaming PUT) | As requested |
| 11 Extension, 12 MIME, 13 Magic bytes, 14 Filename and key | P11 | One pure package, one test table; separate phases would each be under a day |
| 16 SHA-256 identity | P12 | Placed before scanning because every later phase reads the identity |
| 21 Job queue, 22 Worker architecture | P13 | The queue helper and the first worker loop are one deliverable |
| 17 ClamAV, 52 EICAR tests | P14 | The EICAR test is the acceptance test of the ClamAV phase |
| 18 YARA-X, 53 YARA tests | P15 | Same reasoning |
| 15 Archive inspection, 51 zip-bomb tests | P16 | Same |
| 19 Findings model | P17 (findings persistence and format checks: PDF, OOXML, image, polyglot) | Adds the format checks the spec lists under step 15 |
| 20 Decision engine | P18 | As requested |
| 25 AES-256-GCM, 26 Envelope and keys | P19 | One packages/crypto deliverable |
| 23 Exact-version promotion, 24 TOCTOU protection, 27 Clean storage | P20 | These are one code path; promotion without binding is the baseline, built in P32 |
| 29 Audit logging, 30 Hash chain | P21 | Built early (P3 creates the tables) and completed here with checkpoints |
| 28 IAM separation (local), 49 IAM negative tests | P22 (local credentials + DB roles), P29 (AWS/GCP) | Local first, cloud after deployment |
| 47 Unit, 48 Integration, 55 End-to-end | P23 | Tests are written in every phase; P23 assembles the lifecycle and chaos suites and the SQL invariant |
| 31 AWS S3, 58 AWS deployment, 60 Terraform | P24 (account hygiene and budgets), P25 (Terraform S3, IAM, SSM) | Budgets before any other resource |
| 32 GCS replication, 33 Cloud IAM, 59 GCP deployment | P26 (Terraform GCS, WIF), P27 (replication service), P28 (audit checkpoints to both clouds) | As requested, ordered so the service is built against real GCS |
| 45 Metrics and observability | P30 | After the cloud path exists, so metrics cover it |
| 34–43 Dashboard | P31 (foundation + auth), P33 (overview, files, file detail, scans, decision detail), P34 (review, policies, integrity, audit, access) | Three phases instead of ten; each page is a checklist item inside |
| 57 Baseline comparison, 50 TOCTOU harness | P32 | The baseline promoter and the race harness are one experiment artifact |
| 46 Security corpus, 54 API security tests | P35 (corpus generators + full 80-test matrix) | The corpus is needed by P14–P18 in part; P35 completes it and freezes it |
| 56 Performance | P36 | As requested |
| 61 Hardening, 62 Production-like | P37 | Container hardening, dependency scanning, Level C notes |
| 63 Research evaluation, 66 Evidence collection | P38 | One reproducible make reproduce |
| 64 Documentation, 65 Final demonstration | P39 | As requested |

### 2.2 Phase contracts (summary form)

Each entry: objective · inputs → outputs · depends on · security objective · research objective · Definition of Done · commit. Branch name is phase/<n>-<slug>; every phase ends with one squash-merged pull request so that reverting a phase is one git revert.

P0 — Architecture freeze and decisions. Confirm Part 1, answer OPEN-1–4, write docs/adr/0001-0010, threat model and the T1–T8 taxonomy, docs/decision-register.md and docs/risk-register.md as living files. → Depends on nothing. Security: threat model reviewed. Research: hypotheses H1–H5 frozen with their statistics. DoD: ADRs merged; reading list for the four unverified papers assigned. Commit: docs(adr): freeze architecture and decisions.

P1 — Repository and monorepo. pnpm 12 workspace, TypeScript 6.0.3 strict base config, ESLint 10 flat config with typescript-eslint 8.70 and eslint-plugin-boundaries 7.2, Vitest 5, Prettier, .editorconfig, .gitattributes (LF), CI workflow running lint, typecheck, unit tests, gitleaks. → Outputs: empty services/api, packages/shared that build. Security: secret scanning on from the first commit. DoD: CI green on empty workspace; a deliberate boundary violation fails lint. Commit: chore: scaffold monorepo.

P2 — Development environment and Docker Compose. Compose with postgres:18-alpine, localstack/localstack:2026.08.3 (S3 only, SERVICES=s3), fsouza/fake-gcs-server:1.56.1, init containers that create the three buckets with versioning, plus the storage assumption spike (packages/storage/test/assumptions.test.ts): PutObject returns VersionId; If-None-Match: * returns 412 on repeat; GetObject by old VersionId after overwrite returns the old bytes; ChecksumAlgorithm: SHA256 round-trips; fake-gcs honours ifGenerationMatch: 0. If LocalStack fails any assertion, switch to SeaweedFS in this phase and record it in DEC-002. Security: deploy.resources.limits, read_only, cap_drop, no-new-privileges on every service from the start. DoD: docker compose up -d healthy; spike passes; OPEN-2 closed. Commit: chore(compose): local environment with S3 and GCS emulators.

P3 — PostgreSQL schema and migrations. node-pg-migrate 9 (ESM) with plain SQL files 001_types.sql … 009_roles_grants.sql; the sixteen tables from the specification (users, applications, api_keys, security_policies, refresh_tokens, upload_sessions, files, file_versions, cloud_objects, scan_jobs, scan_results, security_decisions, promotion_jobs, replication_jobs, audit_events, audit_checkpoints) with uuidv7() defaults; forbid_mutation trigger; audit_append(); six database roles. Kysely types generated from the schema. Security: append-only evidence and role grants exist before any service code. DoD: migrate from empty; db-01 role test passes; CHECK (storage_version_id NOT IN ('', 'null')) proven. Commit: feat(db): schema, audit chain and roles.

P4 — Configuration and secrets. zod-validated environment loader (packages/shared/config.ts) that refuses to start on a missing variable; Docker file secrets (/run/secrets/*) for pepper, JWT Ed25519 key, KEK, checkpoint key, per-service storage keys; scripts/gen-secrets.sh; .env.example with names only. Security: no secret in git, image or bundle; gitleaks proves it. DoD: missing secret aborts start with a clear message; secrets are never logged (redaction unit test). Commit: feat(config): validated config and secret loading.

P5 — Fastify API foundation, health and readiness. App factory, request-ID, problem+json errors, @fastify/helmet, @fastify/rate-limit, @fastify/swagger generating docs/openapi.json, /healthz, /readyz (DB + storage reachability without detail). DoD: curl /readyz returns 200 only when PostgreSQL and LocalStack answer; OpenAPI file generated in CI. Commit: feat(api): server foundation with health checks.

P6 — Application authentication and API keys. sug_<env>_<prefix8>_<secret43> format, HMAC-SHA-256 with pepper, timingSafeEqual, scopes, revocation, POST /applications, POST /applications/:id/api-keys, DELETE /api-keys/:id, scripts/seed.ts. Security: constant-time verification; AUTH_FAILED audited. DoD: authz-01, authz-02 pass. Commit: feat(auth): application API keys.

P7 — Users, JWT and RBAC. argon2id users, POST /auth/login, rotating refresh tokens in HttpOnly; Secure; SameSite=Strict cookie, EdDSA access tokens with aud=sug-dashboard, roles admin | analyst | auditor, requireRole() guard. Security: RFC 8725 validation (fixed algorithm, iss, aud, exp, typ); lockout after 5 failures. DoD: authz-04 (JWT abuse) and authz-06 (role denial) pass. Commit: feat(auth): dashboard users, JWT and RBAC.

P8 — Policy engine and upload session. packages/policy-engine (zod strict schema sug.policy/v1, canonical JSON + SHA-256, presets, precheck(), filename normaliser), POST /policies, GET /policies/:id, PUT /policies/:id (new version), POST /upload/session issuing the single-use EdDSA upload token (aud=sug-upload, jti, sid, 10 min). DoD: policy-01, policy-02, val-02, val-05, val-09 pass at API level. Commit: feat(upload): policies and upload sessions.

P9 — Storage provider and quarantine bucket. packages/storage StorageProvider interface with S3Provider (AWS SDK v3, works against LocalStack and AWS), putIfAbsent() (IfNoneMatch: '*', ChecksumAlgorithm: 'SHA256'), getByVersion(), head(); per-service credentials from environment; quarantine key scheme incoming/<app_id>/<upload_id>. DoD: spike from P2 passes through the provider; error mapping (412 → AlreadyExists, 404 NoSuchVersion → VersionMissing) unit-tested. Commit: feat(storage): S3 provider with write-once and version reads.

P10 — Streaming upload and resource limits. PUT /upload/:id: atomic session claim, raw body stream, byte counter and SHA-256 tee, abort above min(maxFileSize, declared), 30 s idle timeout, 202 with fileId; transaction inserting files, file_versions, scan_jobs; GET /upload/:id/status. Security: no buffering, no multipart, no temp files. DoD: val-10 (lying size) returns 413 with flat RSS; authz-05 (token reuse race) yields exactly one object; file_versions.storage_version_id populated. Commit: feat(upload): streaming quarantine upload.

P11 — Deterministic validators. packages/security-engine: filename safety, extension allowlist and double-extension denylist, declared MIME, magic detection with file-type 22 (fileTypeFromBuffer on the first 4,100 bytes) and libmagic (file --mime-type -b in the scanner image), type-map.ts canonical types, consistency rule, size rule. Pure functions, table-driven tests. DoD: val-03, val-04, val-06, val-07, val-08, val-12 pass as unit tests; 100% branch coverage on type-map consistency. Commit: feat(security-engine): filename, extension, MIME and magic validators.

P12 — SHA-256 artifact identity. ArtifactIdentity type and helpers in packages/shared; ingest hash at upload; scanned_* columns on findings; identity comparison utility with timingSafeEqual; identity shown in GET /upload/:id/status. Research: this is the object the whole paper is about; unit tests document each field's source. DoD: identity captured at upload and readable; comparison utility tested for every mismatch class. Commit: feat(identity): bound artifact identity.

P13 — PostgreSQL job queue and worker architecture. packages/shared/jobs.ts (claim() with FOR UPDATE SKIP LOCKED, backoff, reaper, DEAD after max_attempts), services/scanner skeleton that claims scan_jobs, fetches by VersionId into a per-job tmpfs directory, hashes, and persists a placeholder finding. DoD: two workers never claim one job (test with 50 jobs and 4 workers); a killed worker's job is re-queued by the reaper within 5 minutes. Commit: feat(worker): PostgreSQL job queue and scanner loop.

P14 — ClamAV integration and EICAR test. clamav/clamav:1.4.6 service on network scan with CLAMD_CONF_* overrides (StreamMaxLength 55M, MaxFileSize 55M, MaxScanSize 200M, MaxRecursion 10, MaxFiles 2000, MaxScanTime 60000, AlertExceedsMax yes, AlertEncrypted yes, AlertEncryptedArchive yes, MaxThreads 4, ConcurrentDatabaseReload no), 4 GB limit, clamdcheck.sh health; packages/scanner/clamav.ts INSTREAM client (zINSTREAM\0, 4-byte big-endian chunks, zero-length terminator, only stream: OK is clean); signature-age gauge. DoD: scan-01 (EICAR assembled at runtime), scan-02, scan-07 (kill clamd mid-scan → ERROR, never ALLOW), scan-09, scan-10 pass. Commit: feat(scanner): ClamAV INSTREAM scanning.

P15 — YARA-X integration. yr 1.20.0 binary in the scanner image; packages/scanner/yara.ts running yr scan --output-format ndjson --timeout 30 --print-meta rules/ <file>, parsing NDJSON, rule meta tags severity and confidence; rules directory versioned, signature_version = git SHA; benign-corpus gate fp-01 before a rule may block. DoD: scan-03 passes; a rule with a syntax error fails the build. Commit: feat(scanner): YARA-X rules.

P16 — Archive inspection and zip-bomb tests. packages/security-engine/archive: yauzl lazy read, two-phase budgets, overlap detection, structural checks (single EOCD, central equals local, no duplicates, methods 0/8, no encryption flag, path and symlink rules, CRC), worker-thread memory cap, OOXML always inspected. DoD: arc-01 to arc-09 pass; arc-02 completes under 10 s with worker RSS under 256 MB. Commit: feat(security-engine): safe ZIP inspection.

P17 — Findings model and format checks. Finalise scan_results writing (one row per check with identity), reason-code table, PDF active-content check (qpdf normalise + keyword scan), OOXML macro and external-relationship check, image trailing-data and embedded-signature check, basic polyglot check, GET /scans/:id. DoD: scan-04, scan-05, scan-06, poly-01, poly-02, poly-03 pass; poly-04 recorded as a documented miss. Commit: feat(scanner): findings persistence and format checks.

P18 — Deterministic decision engine. packages/decision-engine: decide(policy, fileVersion, findings), rules R1–R7 with the R2/R3 precedence, risk score lookup, explainable record sug.decision/v1, property test "any ERROR on a required check never yields ALLOW", GET /security-decisions/:id, review endpoint. DoD: 100% branch coverage; property test passes 10,000 cases; policy-03 passes end to end. Commit: feat(decision): deterministic decision engine.

P19 — AES-256-GCM envelope encryption and key management. packages/crypto: SUG1 format, per-file DEK and nonce, AAD binding, LocalKeyProvider (Docker secret / SSM), KmsKeyProvider stub behind the interface, verify-before-release decrypt. DoD: crypto-01 to crypto-04 pass; test vectors stored; nonce-uniqueness test over 10,000 encryptions. Commit: feat(crypto): envelope encryption.

P20 — Bound promotion and trusted clean storage. services/promotion: decision loop, promotion_jobs insert function that checks ALLOW and non-supersession, re-fetch by bound_storage_version_id, re-hash and size compare, encrypt to temp, putIfAbsent to objects/<app_id>/<file_id>, cloud_objects row, audit in one transaction; GET /files/:id download with verify-before-release and safe headers; DELETE /files/:id. DoD: toctou-01 to toctou-04 pass; int-01 invariant returns zero orphans after the suite; authz-07 passes. Commit: feat(promotion): version- and hash-bound promotion.

P21 — Audit chain completion. Chain verifier packages/audit/verify.ts, GET /security-events, GET /audit/verify, checkpoint signer (Ed25519) writing to the local audit bucket, every action code from the specification wired in. DoD: audit-01 to audit-03 pass; tamper-as-superuser detected at the right seq. Commit: feat(audit): chain verification and checkpoints.

P22 — Local privilege separation. One access-key pair per service in LocalStack (or SeaweedFS identities if OPEN-2 chose it), six PostgreSQL roles wired to the six services, network segmentation (edge, data, store, scan, egress), scanner container read-only and egress-less. DoD: db-01 passes; scanner container cannot reach the internet (test with wget inside it); each service starts with only its own credentials. Commit: feat(iam): local credential and network separation.

P23 — Integration, chaos and end-to-end suites. tests/integration/lifecycle.test.ts (upload → promoted, upload → blocked, upload → review → allow), chaos.ts (kill scanner, kill DB, stop storage mid-flight, duplicate jobs, 1,000 concurrent uploads), invariants.sql run after every suite, packages/sdk client used by tests. DoD: H2 pre-check: zero invariant violations across all chaos runs locally. Commit: test: lifecycle, chaos and invariant suites.

P24 — AWS account hygiene and cost guardrails. Manual console steps (root MFA, no root keys, billing alerts preference, admin IAM identity with MFA), AWS CLI v2 install and aws sts get-caller-identity, Terraform budgets.tf (aws_budgets_budget $5 and $0.01, aws_cloudwatch_metric_alarm on EstimatedCharges via us-east-1 alias, aws_ce_anomaly_monitor + subscription). DoD: a test budget notification e-mail received; terraform plan shows no compute, no NAT, no data events. Commit: feat(infra): AWS budgets and billing alarms.

P25 — AWS storage and IAM with Terraform. aws_s3_bucket × 3 with random_id suffix, aws_s3_bucket_versioning, aws_s3_bucket_lifecycle_configuration, aws_s3_bucket_public_access_block (all four true), aws_s3_bucket_ownership_controls, aws_s3_bucket_server_side_encryption_configuration, aws_s3_bucket_object_lock_configuration (audit bucket, object_lock_enabled = true on the bucket), aws_s3_bucket_policy with the explicit denies, seven aws_iam_role + aws_iam_policy + attachments, seven bootstrap aws_iam_user with sts:AssumeRole only (access keys created by CLI, DEC-013), aws_ssm_parameter SecureString KEK using value_wo; packages/storage/aws-credentials.ts with fromTemporaryCredentials refreshing hourly; Compose profile cloud. DoD: full lifecycle against real S3; toctou-05 (write-once by policy) passes; CloudTrail event history shows role sessions. Commit: feat(infra): AWS buckets, roles and policies.

P26 — Google Cloud storage and Workload Identity Federation. Manual gcloud projects create + billing link + budget (DEC-014); Terraform google_project_service, google_storage_bucket (us-east1, uniform access, public access prevention enforced, versioning, retention 30 days unlocked, soft delete default), google_service_account × 2, google_iam_workload_identity_pool + _provider with aws { account_id } and attribute condition on the replication role, google_service_account_iam_member (roles/iam.workloadIdentityUser for the principalSet), google_storage_bucket_iam_member (objectCreator, objectViewer), google_billing_budget; gcloud iam workload-identity-pools create-cred-config … --aws. DoD: from the laptop with STS env vars, gcloud storage or a 10-line Node script writes one object as sug-replicator and cannot read it back. Commit: feat(infra): GCS replica bucket and federation.

P27 — Replication service. services/replication: claim replication_jobs, stream ciphertext by clean VersionId, file.save(stream, {preconditionOpts: {ifGenerationMatch: 0}, validation: 'crc32c'}), SHA-256 compare with cloud_objects.sha256_cipher, record generation, backoff over 24 h; verify-replica sampling script under sug-auditor. DoD: promoted file appears in GCS within 60 s; iam-08 passes; GCS outage simulation leaves the primary path green. Commit: feat(replication): write-once ciphertext replica.

P28 — Cross-cloud audit checkpoints and restore drill. Checkpoints written to the S3 Object Lock bucket and to GCS every 10 minutes; scripts/restore-from-gcs.ts; scripts/cloud-cleanup.ts; scripts/cloud-inventory.ts. DoD: audit-04 (checkpoint deletion denied) passes; restore drill recovers a file into an empty bucket with a matching plaintext hash. Commit: feat(audit): cross-cloud checkpoints and restore.

P29 — Cloud IAM negative tests and blast radius. tests/security/iam/blast-radius.ts assuming each of the seven roles and attempting the 40-action list on AWS and GCS; cross-check against CloudTrail; tighten policies until zero forbidden successes. DoD: iam-01 to iam-10 pass on real clouds; H4 dataset produced. Commit: test(iam): cloud blast-radius suite.

P30 — Metrics and observability. @prometheus-io/client registry in packages/shared/metrics.ts, the 17 sug_* metrics, /metrics bound to the data network, Prometheus + Grafana in profile obs, the nine alert rules, alert drill. DoD: every required metric visible; HashOrVersionMismatch and AuditChainBroken fire in a drill. Commit: feat(observability): metrics and alerts.

P31 — Dashboard foundation and authentication. apps/dashboard with create-next-app (Next 16, TypeScript, Tailwind 4, App Router), shadcn init, layout shell, login page calling POST /auth/login, token kept in memory and refreshed through the cookie, proxy.ts guarding /dashboard/*, typed API client generated from docs/openapi.json. Security: no server-side secrets; CSP via next.config.ts headers; API base URL from public env. DoD: login, refresh, logout and role-aware navigation work; dashboard container image contains no secret. Commit: feat(dashboard): Next.js foundation and auth.

P32 — Baseline promoter and TOCTOU attack harness. tests/security/toctou/baseline-promoter.ts (P0 key-only, P1 version-only, P2 hash-only), race.ts with deterministic hook points and random delays, 1,000 trials per promoter per window, CSV output, run on LocalStack and on S3 with the write-once policy removed on a scratch bucket. DoD: toctou-06 produces the H3 table; the bound promoter shows zero unscanned promotions. Commit: test(toctou): baseline promoters and race harness.

P33 — Dashboard: overview, files, file detail, scans, decisions. /dashboard, /dashboard/files, /dashboard/files/[id] (timeline with the bound tuple at each stage), /dashboard/scans, decision detail component. DoD: an analyst can trace one file from session to replica; every page has loading, empty and error states. Commit: feat(dashboard): overview, files and decisions.

P34 — Dashboard: review, policies, integrity, audit, access. /dashboard/review, /dashboard/policies (JSON diff between versions), /dashboard/integrity, /dashboard/audit, /dashboard/access. DoD: review flow inserts a superseding decision that still passes promotion checks; integrity page shows chain and checkpoint status. Commit: feat(dashboard): review, policies, integrity, audit, access.

P35 — Security corpus and full test matrix. tests/fixtures/generate.ts (all classes, EICAR assembled at runtime, Mitra-generated polyglots with inert payloads, small bombs), manifest.csv, remaining API security tests (dos-01 to dos-06), security-matrix.csv emitted in CI. DoD: all 80 tests pass or are documented misses; corpus frozen with hashes. Commit: test(security): complete corpus and matrix.

P36 — Performance testing. k6 2.2 scripts for C0–C3, resource logger, full grid locally, reduced grid in the cloud, CSV and plots. DoD: perf-01 to perf-08 data collected; targets confirmed or revised in writing. Commit: test(perf): load and resource measurements.

P37 — Hardening and production-like notes. Image digest pinning, pnpm audit --prod, Trivy scan of images, seccomp review, dependency update policy, Level C documentation (Fargate, RDS, account-per-zone, KMS, compliance-mode Object Lock). DoD: zero high-severity findings in pnpm audit and Trivy; Level C documented with cost. Commit: chore(security): hardening and Level C notes.

P38 — Research evaluation and evidence. H1 configuration sweep, H2 chaos invariant, H3 from P32, H4 from P29, H5 from P36; statistics scripts; make reproduce; evidence folder with screenshots, CloudTrail exports, logs. DoD: one command regenerates every table and figure. Commit: docs(evaluation): reproducible experiments.

P39 — Documentation, demonstration and paper. README quick start (timed under 15 minutes), integration guide, runbook per alert, docs/openapi.json, demo script, paper draft. DoD: a new developer completes the quick start unaided; tagged v1.0.0. Commit: docs: release documentation.

### 2.3 Failure matrix (fail-closed, applies from P18 onward)

| Failure | State | Detail |
| --- | --- | --- |
| Database unavailable at upload | Upload refused 503 | Nothing stored; no orphan object because the DB transaction precedes the response and the object expires in 7 days |
| Database unavailable mid-scan | Job re-queued by reaper | No result, no decision |
| Scanner (clamd) unavailable | ERROR / SCANNER_UNAVAILABLE, 3 retries, then stays ERROR | Never ALLOW |
| Scanner timeout | ERROR / SCAN_TIMEOUT ×3 then QUARANTINE | Slow files go to review |
| Scanner limit exceeded | QUARANTINE / SCANNER_LIMIT_EXCEEDED | Or BLOCK per policy |
| Unknown or undetermined type | QUARANTINE / TYPE_UNDETERMINED |  |
| Detector disagreement | QUARANTINE / DETECTOR_DISAGREEMENT |  |
| Hash mismatch at promotion | BLOCK / HASH_MISMATCH | CRITICAL audit, metric |
| Version missing or mismatch | BLOCK / VERSION_MISMATCH |  |
| Result identity mismatch | BLOCK / RESULT_IDENTITY_MISMATCH | Rule R1 |
| Required check missing | ERROR / REQUIRED_CHECK_MISSING | Rule R2 |
| Storage write failure (clean) | Promotion job retries; decision stands | File stays PROMOTING |
| Storage write failure (quarantine) | Upload 503 |  |
| Encryption failure or KEK unavailable | Promotion job retries; never promotes plaintext |  |
| Policy unavailable | Session 409 NO_ACTIVE_POLICY |  |
| YARA failure (binary missing, rule compile error) | ERROR on yara.rules | Build fails first |
| Archive limit or ambiguity | BLOCK |  |
| Encrypted content | BLOCK / ENCRYPTED_CONTENT |  |
| Replication failure | Clean object remains valid; job retries up to 24 h; alert |  |
| GCS unavailable | Same as above |  |
| Audit insert failure | The surrounding transaction rolls back | No unaudited transition |
| Chain verification fails | Alert AuditChainBroken; uploads continue | Detectable, not preventable |
| Signatures stale > 7 days | ERROR / SCANNER_UNAVAILABLE |  |
| Human review ALLOW | Still passes promotion verification |  |

## Part 3 — Compatibility and documentation verification matrix

Every row was checked on 22 September 2026 against the source in the last column: the npm registry JSON for versions, engines and licence, and official documentation or repository source for behaviour. Rows marked UNVERIFIED must be re-checked in the phase that first uses them before any instruction is followed.

### 3.1 Runtime and tooling

| Item | Verified version | Node 24 | Licence | Notes | Source |
| --- | --- | --- | --- | --- | --- |
| Node.js 24 | Active LTS; maintenance from 20 Oct 2026; EOL 30 Apr 2028 | — | MIT-style | Node 26 is Current, LTS from 28 Oct 2026 | nodejs.org releases |
| pnpm | 12.5.1 | yes | MIT | Native executable; Corepack still bundled in Node 24, removed in 25+ | pnpm installation, Corepack |
| TypeScript | 6.0.3 pinned (7.0.2 exists; no programmatic API yet) | yes | Apache-2.0 | typescript-eslint peer <6.1.0 | TS 7.0 announcement |
| ESLint | 10.11.0; flat config only | ≥ 20.19 | MIT | ESLint 9 EOL 6 Aug 2026 | ESLint v10 |
| typescript-eslint | 8.70.1 | yes | MIT | peer eslint ^8.57 ‖ ^9 ‖ ^10 | dependency versions |
| eslint-plugin-boundaries | 7.2.0 | ≥ 18.18 | MIT | Flat-config usage documented; ESLint 10 support not stated (UNVERIFIED, test in P1) | npm registry |
| Vitest | 5.0.1 | ^22.12 ‖ ^24 ‖ ≥26 | MIT | clearMocks default true; strict locators | Vitest 5 blog |
| tsx | 4.23.15 | yes | MIT | Dev only | npm registry |
| @types/node | 24.13.6 (Node 24 line) | — | MIT | Pin the 24.x line | npm registry |
| Docker Compose | v2 (spec) | — | Apache-2.0 | deploy.resources.limits applied by docker compose up; secrets file mounts; read_only, cap_drop, security_opt, tmpfs all in the spec | Compose deploy, services, secrets |

### 3.2 API service

| Package | Version | Node 24 | Licence | Notes | Source |
| --- | --- | --- | --- | --- | --- |
| fastify | 5.12.5 | tested 20/22/24/26 | MIT | Fastify 6 alphas exist; 6 will drop Node 20/22 | Fastify LTS |
| @fastify/type-provider-zod | 1.0.0 | yes | MIT | peer fastify ^5.5, zod ≥ 4.2, @fastify/swagger ≥ 9.5.1; unscoped fastify-type-provider-zod 7.0 also exists, not chosen | npm registry |
| zod | 4.6.5 | yes | MIT | v4 API: z.email(), z.uuid(), z.strictObject(), error not message | zod v4 changelog |
| @fastify/rate-limit | 11.2.0 | yes | MIT |  | npm registry |
| @fastify/helmet | 13.1.1 | yes | MIT | helmet ^8 | npm registry |
| @fastify/cors | 11.3.0 | yes | MIT |  | npm registry |
| @fastify/cookie | 11.1.2 | yes | MIT |  | npm registry |
| @fastify/swagger | 9.8.2 | yes | MIT | OpenAPI 3.1 output | npm registry |
| pino / pino-pretty | 10.3.1 / 13.1.3 | yes | MIT |  | npm registry |
| @prometheus-io/client | 0.16.1 | ^22 ‖ ^24 ‖ ≥26 | Apache-2.0 | Replaces deprecated prom-client | npm registry |
| jose | 6.2.12 | yes (WebCrypto Ed25519) | MIT | EdDSA and Ed25519 alg names supported | jose README |
| argon2 | 0.45.1 | ≥ 16.17; prebuilt Node-API binaries | MIT | Fallback @node-rs/argon2 2.2.1 | node-argon2 |
| kysely | 0.29.6 | ≥ 22 | MIT |  | npm registry |
| pg | 8.23.0 | yes | MIT |  | npm registry |
| node-pg-migrate | 9.0.0 | ≥ 20.11; ESM | MIT | Plain SQL migrations supported | npm registry |

### 3.3 Scanner and file handling

| Item | Version | Node 24 | Licence | Notes | Source |
| --- | --- | --- | --- | --- | --- |
| file-type | 22.1.1 | ≥ 22; ESM-only | MIT | API is fileTypeFromBuffer etc.; 2026 ZIP-bomb and ASF advisories fixed in current line | file-type readme |
| yauzl | 3.4.0 | yes | MIT | Maintained (June 2026) | npm registry |
| @zip.js/zip.js | 2.17.0 | ≥ 18 | BSD-3 | Alternative | npm registry |
| sharp | 0.35.4 | ≥ 20.9; libvips ≥ 8.18.6 prebuilt | Apache-2.0 | pnpm must install optional deps | sharp install |
| ClamAV image | clamav/clamav:1.4.6 (LTS to 15 Aug 2027); 1.5.4 is regular | — | GPLv2 | CLAMD_CONF_<Option> env overrides; clamdcheck.sh health; 3–4 GiB RAM | ClamAV Docker, EOL |
| clamd protocol | INSTREAM framing, stream: OK | — | — | z or n prefix mandatory for INSTREAM | clamd protocol, clamd.8 |
| clamd.conf options | All eleven names used exist with the defaults quoted in the spec | — | — |  | clamd.conf.sample |
| clamscan npm | 2.4.0 (Oct 2024) | yes | MIT | Not chosen; in-house client | npm registry |
| YARA-X | 1.20.0 CLI; yr scan --output-format ndjson; exit code 0/1 only | — | BSD-3 | Install from GitHub release binary or cargo install yara-x-cli; pip install yara-x is the Python binding, not the CLI | YARA-X CLI, installation |
| @virustotal/yara-x npm | 1.20.0 (WASM) | yes | BSD-3 | Fallback; no production statement | npm registry |
| qpdf, file (libmagic) | Distro packages in the scanner image (Alpine qpdf, file) | — | Apache-2.0, BSD-2 | Versions resolved at image build; pin the Alpine base digest | — |
| Magika, PolyFile | 1.0.3 (pip) / 0.6.0 (pip) | — | Apache-2.0 | Optional, advanced only | Magika, PolyFile |

### 3.4 Storage, cloud SDKs and emulators

| Item | Verified fact | Status | Source |
| --- | --- | --- | --- |
| MinIO | Repository archived April 2026; community distributed as source only; minio/minio on Docker Hub returns 404; last release Oct 2025 | Not usable | MinIO README, releases |
| LocalStack Community | localstack/localstack:2026.08.3; PutObject IfNoneMatch since 3.7.0, IfMatch since 4.0.3; S3 in the free tier | Chosen; IAM enforcement in Community: VERIFICATION REQUIRED (P2); Object Lock coverage UNVERIFIED | v3.7.0, S3 docs |
| SeaweedFS | 4.45; versioning, Object Lock, conditional headers; If-None-Match: * bug on versioned buckets fixed Jan 2026 | Fallback | S3 versioning wiki |
| fake-gcs-server | 1.56.1; JSON-API ifGenerationMatch, generations, declared CRC32C honoured; XML path not | Chosen (JSON only) | upload.go |
| @aws-sdk/client-s3 | 3.1137.0; PutObjectCommand accepts IfNoneMatch, IfMatch, ChecksumAlgorithm: 'SHA256', returns VersionId, ChecksumSHA256; GetObjectCommand accepts VersionId, ChecksumMode | Verified from SDK source | models_0.ts |
| @aws-sdk/credential-providers | fromTemporaryCredentials({params: {RoleArn, DurationSeconds}}) | Verified | README |
| @aws-sdk/client-ssm, client-kms | GetParameterCommand({Name, WithDecryption}); GenerateDataKeyCommand({KeyId, KeySpec: 'AES_256', EncryptionContext}) | Verified | SDK source |
| @google-cloud/storage | 8.2.0; Node ≥ 22; file.save(data, {preconditionOpts: {ifGenerationMatch: 0}, validation: 'crc32c', metadata}) | Verified from source | file.ts |
| google-auth-library | 11.1.0; external-account config with AWS credential source reads AWS_* env vars before IMDS | Verified | AIP-4117 |
| S3 conditional writes | If-None-Match: * → 412 if exists, 409 on conflict; policy keys s3:if-none-match, s3:if-match, s3:ObjectCreationOperation; enforcing breaks CopyObject | Verified | conditional writes, enforce |
| S3 permissions | GetObject with versionId needs s3:GetObjectVersion; permanent delete needs s3:DeleteObjectVersion; governance bypass needs s3:BypassGovernanceRetention | Verified | GetObject, policy actions |
| aws:PrincipalArn | Returns the role ARN for role sessions, not the session ARN | Verified | condition keys |
| SSM SecureString | With the AWS-managed aws/ssm key no explicit kms:Decrypt is needed | Verified | Parameter Store access |
| STS AssumeRole by IAM user | Trust policy principal = user ARN; user also granted sts:AssumeRole | Verified (whether the identity grant can be omitted same-account: UNVERIFIED; grant both) | switch-role permissions |
| GCS preconditions | ifGenerationMatch=0 → 412 if a live object exists; objectCreator lacks storage.objects.delete so cannot overwrite | Verified | objects.insert, IAM roles |
| GCS retention + versioning | Coexist; overwrite under retention → 403 retentionPolicyNotMet | Verified | Bucket Lock |
| WIF cred config | gcloud iam workload-identity-pools create-cred-config … --aws --service-account=… --output-file=…; no key material in the file | Verified | WIF other clouds |

### 3.5 Infrastructure as code

| Item | Verified fact | Source |
| --- | --- | --- |
| Terraform | 1.16.1; BUSL-1.1. OpenTofu 1.12.6 (MPL-2.0) as drop-in | Terraform releases, OpenTofu |
| AWS provider | 6.58.0; aws_s3_bucket inline blocks deprecated (use separate resources); bucket_region attribute replaces region on the bucket; object_lock_enabled on aws_s3_bucket for new buckets | v6 upgrade guide |
| aws_s3_bucket_lifecycle_configuration | expiration { days } and expired_object_delete_marker must be separate rules; filter required | provider docs |
| aws_s3_bucket_public_access_block | All four flags default false; set all true | provider docs |
| aws_iam_role | inline_policy, managed_policy_arns deprecated; use aws_iam_role_policy / attachment | provider docs |
| aws_iam_access_key | Secret written to state in plaintext unless pgp_key | provider docs; hence DEC-013 |
| aws_ssm_parameter | SecureString value in state unless value_wo | provider docs |
| aws_budgets_budget, aws_cloudwatch_metric_alarm, aws_ce_anomaly_monitor/subscription | Exist with the arguments used in P24 | provider docs |
| Google provider | 8.1.0 (7.x still patched); no breaking change to the resources used | releases |
| google_storage_bucket | uniform_bucket_level_access, public_access_prevention = "enforced", versioning {enabled}, retention_policy {retention_period, is_locked}, soft_delete_policy {retention_duration_seconds}, lifecycle_rule | provider docs |
| google_iam_workload_identity_pool_provider | aws { account_id }, attribute_condition, attribute_mapping | provider docs |
| google_project | TF docs say an Organization is required; API allows none | Hence DEC-014 |
| google_billing_budget | Needs billing_project + user_project_override = true with user ADC | provider docs |

### 3.6 Frontend

| Item | Version | Notes | Source |
| --- | --- | --- | --- |
| Next.js | 16.3.5 | Node ≥ 20.9; Turbopack default; next.config.ts supported, .cjs/.cts not; next build no longer lints; middleware renamed proxy; async params | installation, next.config |
| React | 19.3.0 |  | react.dev |
| Tailwind CSS | 4.3.3 with @tailwindcss/postcss | postcss.config.mjs, @import "tailwindcss" | Tailwind + Next |
| shadcn CLI | 4.21.0; pnpm dlx shadcn@latest init | Tailwind v4 and React 19 default; toast deprecated for sonner | shadcn Next, Tailwind v4 notes |

### 3.7 Items that remain UNVERIFIED

| Item | Why it matters | Verify in |
| --- | --- | --- |
| LocalStack Community enforces IAM policies on S3 calls | Decides whether local IAM negative tests are meaningful | P2 spike |
| LocalStack Community Object Lock support | Local audit-bucket tests | P2 spike; otherwise audit-04 runs on AWS only |
| eslint-plugin-boundaries with ESLint 10 | P1 lint gate | P1 |
| k6 2.2.0 release date | None (version is current) | — |
| Terraform creating a parentless google_project | Avoided by DEC-014 | — |
| Same-account AssumeRole without identity-policy grant | Avoided by granting both | — |
| Exact MinIO release that fixed If-None-Match: * | Moot after DEC-002 | — |
| Whether the S3 SHA-256 full-object checksum applies to multipart | Moot: multipart disabled | — |

## Part 4 — Risk register

Twenty-two risks, technical and research. Probability and impact are Low, Medium or High. Status is OPEN until the named phase closes it. This table lives on as docs/risk-register.md from P0 and is updated whenever a phase changes it.

| ID | Risk | Prob. | Impact | Mitigation | Detection | Fallback | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | Local S3 emulator (LocalStack) diverges from S3 on version IDs, If-None-Match or checksums | M | H | P2 assumption spike runs before any storage code | Spike failures | SeaweedFS; or develop against a real AWS bucket in dev from P9 | OPEN until P2 |
| R-02 | LocalStack Community does not enforce IAM, so local privilege-separation tests prove nothing | H | M | DEC-003: local separation by credentials only; real tests on AWS in P29 | P2 check | SeaweedFS identities for local enforcement | OPEN until P2 |
| R-03 | ClamAV needs 3–4 GiB; team laptops with 8 GB struggle | M | M | One lab machine runs clamd; ConcurrentDatabaseReload no; MaxThreads 4 | OOM kills in docker compose ps | Point the scanner at a shared clamd over the LAN | OPEN until P14 |
| R-04 | Fail-open bug in decision or promotion code | L | H | Pure decision function; property test; SQL invariant after every suite; two reviewers on packages/decision-engine, packages/crypto, services/promotion | int-01 | Revert the phase | OPEN, re-checked every phase |
| R-05 | Accidental AWS spend (compute, data events, NAT, KMS keys) | M | M | P24 before P25: budgets, zero-spend alert, billing alarm, anomaly detection, region restriction; CI grep for forbidden resource types | Budget e-mail | terraform destroy; cleanup script | OPEN until P24 |
| R-06 | New AWS account on the Free plan closes at 6 months | M | M | Create the account at P24, not P0; calendar reminder at month 5; upgrade to Paid with budgets in place | Warning e-mails at 50/25/10% credits and 15/7/2 days | Export data with cloud-cleanup before closure | OPEN |
| R-07 | Workload Identity Federation configuration stalls | M | L | Time-boxed spike in P26 with the documented create-cred-config --aws path; env-var credential source verified | Token exchange errors | Executable-sourced credentials; never a key file | OPEN until P26 |
| R-08 | KEK loss | L | H | Two offline copies held by two people; restore drill in P28 | Drill failure | None: files are unrecoverable, state this in the runbook | OPEN |
| R-09 | TypeScript or ESLint toolchain drift (TS 7 API, ESLint 10) | M | L | Pin TS 6.0.3 and typescript-eslint 8.70; Renovate with grouped PRs and CI | CI failure | Alias typescript@npm:@typescript/typescript6 | OPEN until P1 |
| R-10 | Upload-path library vulnerabilities | L | M | No multipart parser at all; raw body stream; pnpm audit --prod and Trivy in CI | CI | Patch and redeploy | Mitigated by design |
| R-11 | Scanner container compromised by a hostile file | M | M | Read-only root, non-root, no egress, cap_drop ALL, SCANNER_ROLE cannot write clean or insert decisions | Unexpected egress attempts, AccessDenied in CloudTrail | Rebuild container; re-scan affected files | Mitigated by design; tested in P22, P29 |
| R-12 | Race tests are flaky | M | M | Deterministic hook points in the promoter for the harness, plus randomised runs; 1,000 trials; report intervals | CI variance | Report both deterministic and random results separately | OPEN until P32 |
| R-13 | The four unread papers already cover the claimed gap | M | H | P0 reading list; claims phrased "to the best of our knowledge"; measurement and artifact stand regardless | Supervisor review | Reframe as reproduction and extension | OPEN until P0 |
| R-14 | Corpus built by the same people who built the checks (construct validity) | H | M | Classes derived from FUSE, FUEL, WSTG, ZipDiff; one member writes fixtures blind; misses reported | Peer review | State as limitation | OPEN until P35 |
| R-15 | Scope creep into CDR, ML, sandbox, Kubernetes | H | M | MVP exclusion list; supervisor sign-off for additions; P37 is the only "extra" phase | PR review | Cut advanced items | OPEN |
| R-16 | Next.js dashboard becomes a second backend holding secrets or logic | M | M | DEC-004 constraints; dashboard image scanned for secrets; Route Handlers only forward the JWT | Code review; gitleaks on the image | Replace with static export | OPEN until P31 |
| R-17 | GuardDuty or KMS enabled by mistake in the demo | L | L | Optional resources in separate Terraform files not applied by default | Budget | Disable | Mitigated |
| R-18 | Performance targets unmet on laptops | M | L | Targets are declared before measurement and may be revised in writing; report ratios | P36 data | Revise targets with justification | OPEN until P36 |
| R-19 | LocalStack image size and start time slow CI | M | L | SERVICES=s3; cache image; SeaweedFS if CI time exceeds 10 minutes | CI duration | SeaweedFS | OPEN until P2 |
| R-20 | Windows host path and line-ending issues in Docker bind mounts and scripts | M | L | .gitattributes forces LF; scripts run inside containers; WSL 2 backend | Script failures | Run scripts through pnpm wrappers | OPEN until P1 |
| R-21 | Signature database rate-limited or blocked by the ClamAV CDN | L | M | freshclam only, Checks 12; one private mirror for the team if several machines | 429/403 in freshclam logs | Mount a shared signature volume | OPEN until P14 |
| R-22 | Google project creation blocked (no billing, quota) | L | M | DEC-014: create by hand first; Always Free needs a billing account with a card | gcloud errors | Skip GCS until resolved; replication is asynchronous and optional per policy | OPEN until P26 |

## Part 5 — Final implementation order

Thirty-nine phases in five tracks; the local MVP exists at the end of P23 (about week 13), the cloud MVP at P30, and the research artifact at P38. Dashboard phases run in parallel from P31 without blocking anything. Estimates assume three to four students part-time and are re-planned after P10.

### 5.1 Order and dependencies

flowchart LR
  A[Track 1<br/>P0–P5 foundation] --> B[Track 2<br/>P6–P12 ingest]
  B --> C[Track 3<br/>P13–P23 analysis,<br/>decision, promotion]
  C --> D[Track 4<br/>P24–P30 clouds,<br/>metrics]
  D --> E[Track 5<br/>P32, P35–P39<br/>research + release]
  C -.-> F[Dashboard<br/>P31, P33, P34]
  F -.-> E

| # | Phase | Track | Blocked by | Est. | Milestone |
| --- | --- | --- | --- | --- | --- |
| 0 | Architecture freeze | 1 | — | 1 wk | Decisions closed |
| 1 | Repository and monorepo | 1 | 0 | 2 d |  |
| 2 | Compose and storage spike | 1 | 1 | 3 d | OPEN-2 closed |
| 3 | Schema and migrations | 1 | 2 | 4 d |  |
| 4 | Config and secrets | 1 | 3 | 2 d |  |
| 5 | Fastify foundation, health | 1 | 4 | 2 d | First bootable API |
| 6 | API keys | 2 | 5 | 2 d |  |
| 7 | Users, JWT, RBAC | 2 | 6 | 3 d |  |
| 8 | Policy engine and sessions | 2 | 7 | 4 d |  |
| 9 | Storage provider, quarantine | 2 | 2, 8 | 3 d |  |
| 10 | Streaming upload | 2 | 9 | 4 d | Upload lands in quarantine with a version ID |
| 11 | Validators | 2 | 10 | 4 d |  |
| 12 | Artifact identity | 2 | 11 | 2 d |  |
| 13 | Job queue and worker | 3 | 12 | 3 d |  |
| 14 | ClamAV | 3 | 13 | 4 d | EICAR blocked |
| 15 | YARA-X | 3 | 14 | 2 d |  |
| 16 | Archive inspection | 3 | 15 | 5 d |  |
| 17 | Findings and format checks | 3 | 16 | 4 d |  |
| 18 | Decision engine | 3 | 17 | 4 d |  |
| 19 | Envelope encryption | 3 | 18 | 3 d |  |
| 20 | Bound promotion, clean storage | 3 | 19 | 5 d | Local end-to-end lifecycle |
| 21 | Audit chain completion | 3 | 20 | 3 d |  |
| 22 | Local privilege separation | 3 | 21 | 3 d |  |
| 23 | Integration, chaos, invariant | 3 | 22 | 4 d | Local MVP |
| 24 | AWS hygiene and budgets | 4 | 23 | 2 d |  |
| 25 | AWS storage and IAM (Terraform) | 4 | 24 | 5 d | Real S3 lifecycle |
| 26 | GCS and federation (Terraform) | 4 | 25 | 4 d |  |
| 27 | Replication service | 4 | 26 | 3 d |  |
| 28 | Cross-cloud checkpoints, restore | 4 | 27 | 3 d |  |
| 29 | Cloud IAM negative tests | 4 | 28 | 3 d | H4 data |
| 30 | Metrics and alerts | 4 | 29 | 3 d | Cloud MVP |
| 31 | Dashboard foundation | D | 7 | 3 d | parallel |
| 32 | Baseline promoters and race harness | 5 | 25 | 5 d | H3 data |
| 33 | Dashboard: overview, files, decisions | D | 31, 21 | 5 d | parallel |
| 34 | Dashboard: review, policies, integrity, audit, access | D | 33, 28 | 5 d | parallel |
| 35 | Corpus and full matrix | 5 | 30 | 4 d | 80 tests |
| 36 | Performance | 5 | 35 | 4 d | H5 data |
| 37 | Hardening, Level C | 5 | 36 | 3 d |  |
| 38 | Research evaluation | 5 | 32, 36, 29 | 5 d | make reproduce |
| 39 | Documentation, demo, paper | 5 | 38, 34 | 2 wk | v1.0.0 |

Critical path: 0 → 5 → 10 → 12 → 13 → 20 → 23 → 25 → 30 → 35 → 38 → 39, about 24 weeks. If time runs short, cut in this order: P37 Level C notes, Grafana panels in P30, /dashboard/access in P34, image CDR (never scheduled). Never cut P22, P29, P32 or P38: they are the research.

### 5.2 Git strategy

| Rule | Detail |
| --- | --- |
| Default branch | main, protected: CI required, one review (two for packages/decision-engine, packages/crypto, services/promotion, infrastructure/), linear history |
| Phase branch | phase/<nn>-<slug> from main, e.g. phase/10-streaming-upload |
| Commits inside a phase | Small, Conventional Commits (feat, fix, test, chore, docs, infra); each commit compiles |
| Merge | Squash-merge with the phase commit message from Part 2; tag phase-<nn> on main |
| Rollback point | git revert <squash-sha> restores the previous phase; migrations get a paired down file so the database can follow |
| Secrets | gitleaks pre-commit hook and CI; .env, secrets/, *.tfstate, *.json credential configs in .gitignore |
| Terraform state | Local file under infrastructure/*/state/ (git-ignored) for the demo; remote state is Level C |
| Evidence | docs/evidence/<phase>/ committed with screenshots and CSVs, never raw logs with secrets |

### 5.3 Phase checkpoint template

Every phase ends with this list filled in and pasted into the pull request:

- ☐ Requirement implemented as stated in the phase contract

- ☐ pnpm typecheck and pnpm lint pass

- ☐ pnpm test passes; new tests named in the contract exist

- ☐ Security test(s) for the phase pass

- ☐ Configuration verified with the phase's verification commands and expected output

- ☐ Documentation updated (docs/, ADR if a decision changed, decision and risk registers)

- ☐ No known blocker; UNVERIFIED items listed for the next phase

- ☐ Squash commit created with the phase message; tag applied

### 5.4 Evidence collection plan (per phase)

| Phase | Evidence to save under docs/evidence/ | Paper section |
| --- | --- | --- |
| P2 | Spike output showing version IDs and 412 on second put | Implementation |
| P10 | HeadObjectVersion output and the matching file_versions row | Design: identity |
| P14 | EICAR scan log stream: Eicar-Test-Signature FOUND and the BLOCK record | Evaluation H1 |
| P16 | arc-02 timing and RSS chart | Evaluation H1 |
| P18 | Property-test output (10,000 cases, zero ALLOW on ERROR) | Design: fail-closed |
| P20 | toctou-01–04 outputs; a HASH_MISMATCH decision record | Evaluation H3 |
| P21 | audit/verify output before and after tampering | Design: audit |
| P23 | Chaos run summary with invariants.sql result | Evaluation H2 |
| P25 | terraform plan summary; bucket policy JSON; CloudTrail AssumeRole events | Deployment |
| P26–27 | GCS object listing with generation; replicator 403 on read-back | Multi-cloud |
| P29 | Blast-radius CSV; CloudTrail AccessDenied export | Evaluation H4 |
| P30 | Grafana screenshots of the alert drill | Observability |
| P32 | H3 table: unscanned promotions per promoter per window, with intervals | Evaluation H3 |
| P33–34 | Dashboard screenshots: file timeline, decision detail, integrity page | System overview |
| P35 | security-matrix.csv | Evaluation H1 |
| P36 | perf CSVs and plots | Evaluation H5 |
| P38 | make reproduce log | Reproducibility |

### 5.5 Ready for Phase 0

When you say START PHASE 0, you will receive only Phase 0's full contract: the ADR set to write, the threat model and taxonomy templates, the decision and risk register files, the reading list, the exact repository bootstrap that P1 will build on, verification steps, and the checkpoint. Before that, three answers are useful but not blocking: OPEN-1 (PostgreSQL 18 or 16), OPEN-2 (LocalStack or SeaweedFS, which P2 can settle), and OPEN-3 (the two missing documents).